## Timeline
DBAS27198 - 1265_33418 - Database Design and Implementation |  |  | Project: | Case Study | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07
Task | Start | End | Duration | Responsible
Introductory Message | 2026-07-10 | 2026-07-10 | 1 | Michael | bar: 2026-07-10
Preliminary Project Timeline | 2026-07-11 | 2026-07-11 | 1 | Michael | bar: 2026-07-11
Confirm Timeline Dates & Tasks | 2026-07-11 | 2026-07-13 | 3 | Team | bar: 2026-07-11 to 2026-07-13
Designate Primary & Secondary Responsibilities | 2026-07-13 | 2026-07-13 | 1 | Team | bar: 2026-07-13
Conceptual EER Diagram – Draft | 2026-07-14 | 2026-07-16 | 3 | Michael | bar: 2026-07-14 to 2026-07-16
Conceptual EER Diagram – Review & Update | 2026-07-17 | 2026-07-18 | 2 | Quinn | bar: 2026-07-17 to 2026-07-18
Data Structure Diagram – Draft | 2026-07-19 | 2026-07-22 | 4 | Quinn | bar: 2026-07-19 to 2026-07-22
Project Midway Check Point | 2026-07-21 | 2026-07-21 | 1 | Team | bar: 2026-07-21
Data Structure Diagram – Review & Update | 2026-07-22 | 2026-07-24 | 3 | Mitchell | bar: 2026-07-22 to 2026-07-24
AWS & DB Infrastructure Setup | 2026-07-18 | 2026-07-24 | 4 | Mitchell | bar: 2026-07-19 to 2026-07-21; 2026-07-24
Database Implementation – Draft | 2026-07-25 | 2026-07-26 | 2 | Gagandeep | bar: 2026-07-25 to 2026-07-26
Database Implementation – Review & Finalise | 2026-07-27 | 2026-07-27 | 1 | Sai Krishna | bar: 2026-07-27
Data Insertion | 2026-07-28 | 2026-07-28 | 1 | Gloria | bar: 2026-07-28
SQL Query – Development | 2026-07-29 | 2026-07-29 | 1 | Gagandeep | bar: 2026-07-29
SQL Query – Review & Update | 2026-07-30 | 2026-07-30 | 1 | Gloria | bar: 2026-07-30
Project Submission Package – Draft | 2026-07-31 | 2026-08-01 | 2 | Sai Krishna | bar: 2026-07-31 to 2026-08-01
Project Submission Package – Review & Tweak | 2026-08-02 | 2026-08-03 | 2 | Michael | bar: 2026-08-02 to 2026-08-03
Final Project Review | 2026-08-04 | 2026-08-07 | 4 | Team | bar: 2026-08-04 to 2026-08-07
Formulas:
End = [Start]+[Duration]-1
End = +[End, row above]
Start = [End, row above]+1
Start = [End, row above]

## Responsibilities
S. # | Student Name | Student ID | 1st Responsibility | 2nd Responsibility | Work Completed
1 | Mitchell | 991033735 | Data Structure Diagram – Review & Update | AWS & DB Infrastructure Setup
2 | Michael | 991860679 | Conceptual EER Diagram – Draft | Project Submission Package – Review & Tweak
3 | Gloria | 991840144 | Data Insertion | SQL Query – Review & Update
4 | Sai Krishna | 991823191 | Project Submission Package – Draft | Database Implementation – Review & Finalise
5 | Gagandeep | 991850039 | Database Implementation – Draft | SQL Query – Development
6 | Quinn | 991857752 | Data Structure Diagram – Draft | Conceptual EER Diagram – Review & Update